## Sheet1
Description | Start Date | Duration
Form Team | 2020-10-12 | 1
Establish Team Communication | 2020-10-12 | 1
Set Up GitHub Repositories | 2020-10-12 | 1
First Draft UML Diagram | 2020-10-12 | 1
Decide on a Card Game | 2020-10-13 | 1
Fine-Tune UML Diagram | 2020-10-13 | 2
Discuss Basic Functionality | 2020-10-14 | 2
Final Draft UML Diagram | 2020-10-15 | 1
Create Basic Object Classes | 2020-10-17 | 2
Implement Game Rules | 2020-10-19 | 6
Implement GUI | 2020-10-25 | 8
Testing | 2020-11-02 | 1
Final Changes | 2020-11-03 | 2